Project Status Report

A Scalable Big Data Platform for Real-Time Urban Air Quality Tracking and Public Safety Alerting

23AID302 — Big Data Analytics  |  12 August 2026

# 1. Executive Summary

This report covers a full audit, rebuild and validation of the project dataset, plus the machine-learning pipeline built on top of it. Three things changed materially.

1. The previous model was broken, not merely weak.

The earlier run reported R² = 0.58. Measured on this same data, simply predicting "next hour = this hour" — no model at all — scores R² = 0.8056. The previous pipeline was therefore performing worse than doing nothing. Four root causes were identified and fixed.

2. The dataset has been rebuilt honestly and validated.

The old 23.44 GB file was 66.6% synthetic, and the synthetic rows were measurably easier to predict than the real ones — which inflated every metric. A new 27.48 GB dataset was generated from the real measurements using a disclosed statistical model, and it passes five statistical fidelity tests against the real data.

3. The model now works.

On a chronological hold-out scored on real rows only, the model achieves R² = 0.9201 against a persistence baseline of 0.8984 — an 11.3% reduction in error. Every metric is reported in raw micrograms per cubic metre.

Current position: the data and analytics work is complete and de-risked. The distributed execution (Hadoop/Spark) and the streaming, alerting, serving and dashboard layers have not yet been built. In effort terms, roughly half the project scope remains.

# 2. The Dataset — What Is Actually In It

## 2.1  The original file that was audited

File: final_air_quality_dataset_22gb_balanced.csv

| Property | Documented | Actually measured |
| --- | --- | --- |
| File size | 23.44 GB | 23.44 GB — confirmed |
| Total rows | 48,646,989 | 48,646,989 — confirmed |
| Columns | 102 | 139 — the docs undercount by 37 |
| Monitoring stations | 453 | 453 — confirmed |
| Cities | 241 | 241 — confirmed |
| Master (real) rows | 1,429,563 | 16,252,931 — 11x more real data than documented |
| Synthetic rows | not stated | 32,394,058 (66.59% of the file) |
| Duplicate (station, hour) pairs | not stated | 15 in 48.6 M rows — effectively zero |
| Time span | not stated | 2010 – 2023 |

The most important correction: your report states the master dataset held 1,429,563 rows. A full scan of all 48.6 M rows found 16,252,931 rows tagged as genuinely real. You have eleven times more real data than you believed.

## 2.2  Column audit — why 139 became 32

Fill rates were measured across 960,000 rows sampled from 240 evenly-spaced positions throughout the full 23 GB file. The columns fall into clear groups.

| Group | Count | Evidence | Decision |
| --- | --- | --- | --- |
| Empty / near-empty sensor columns | 69 | 22 of them at exactly 0.000% filled; the rest under 3% | DROP |
| Mechanically duplicated | 14 | bp_(mmhg).1–.7 and rf_(mm).1–.7, all at an identical 0.351% | DROP |
| City-profile constants | 15 | Constant per city; these generated the dynamic columns | DROP |
| Raw meteorology superseded | 6 | Sparse ancestors of 100%-filled dynamic columns | DROP |
| Organic pollutants | 5 | Not AQI parameters; 25–63% filled | DROP |
| Non-predictive metadata | 4 | agency, station_location, to_date, traffic_level | DROP |
| Retained | 32 | Carry genuine, needed signal | KEEP |

The 14 mechanically duplicated columns share an identical fill rate of 0.351%, which is what proves they are fragments of one split column rather than independent instruments.

## 2.3  Measured data coverage of the kept measurements

| Column | Filled | Observed range | Role |
| --- | --- | --- | --- |
| pm25 | 74.26% | 0.01 – 1049.9 | Prediction target + feature |
| pm10 | 67.48% | 0.01 – 1000.0 | AQI pollutant |
| no2 | 78.55% | 0.01 – 498.5 | Traffic / industry tracer |
| so2 | 74.71% | 0.01 – 200.0 | Industrial tracer |
| co | 74.17% | 0.00 – 50.0 | Combustion tracer |
| o3 | 73.92% | 0.01 – 206.9 | Photochemical smog |
| nh3 | 58.99% | 0.01 – 497.9 | Agricultural / waste |
| wd_degree (coalesced) | 74.77% | 0 – 360 | Wind direction |
| solar_radiation | 61.11% | 0 – 1500 | Drives ozone chemistry |
| pressure | 47.05% | 700 – 1100 | Boundary-layer height |
| temperature / humidity / wind / rain | 100% | various | Dynamic weather block |

Only 45.78% of rows carry all seven AQI pollutants simultaneously. Dropping incomplete rows would discard 26.4 million rows, so three-tier median imputation is mandatory — and each imputed value is flagged so measured and filled data stay distinguishable.

## 2.4  Defects found in the original data

| Defect | Evidence | Severity |
| --- | --- | --- |
| is_rush_hour is not binary | 24,725 distinct values instead of 2 (e.g. 1.0282169444321818) | Critical |
| variation_id corrupted | 29,918 distinct values instead of 3 | Critical |
| Impossible humidity | Maximum 104.999% — relative humidity cannot exceed 100 | Moderate |
| Impossible traffic index | Maximum 110.2 on a documented 0–100 scale | Moderate |
| Sparse AQI coverage | Only 45.78% of rows have all 7 pollutants | Moderate |

The cause of the first two is the same: the original expansion script applied ±3% Gaussian noise to every numeric column without excluding binary flags and identifiers. Both defects appear in rows tagged "original" as well as synthetic ones, so they cannot be filtered away by provenance.

# 3. The New Dataset

Location: E:\airquality_expanded  (23 files, part-*.csv)

| Property | Value |
| --- | --- |
| Total size | 27.48 GB |
| Total rows | 146,276,379 |
| Real rows | 16,252,931 (11.1%) |
| Synthetic rows | 130,023,448 (88.9%) |
| Stations | 4,077 (453 real + 3,624 synthetic) |
| Columns | 32 — pruned and repaired |
| Scale factor | 9x |
| Build time | 17 minutes |
| Files | 23 CSV parts, maximum 1.27 GB each |

## 3.1  Complete column reference

| Column | Type | Meaning |
| --- | --- | --- |
| station_id | text | Monitoring station. Synthetic siblings carry a ~Snn suffix |
| state | text | State the station sits in |
| city | text | City the station sits in |
| from_date | timestamp | Hour of observation — the time key |
| pm25 | float | Fine particulate matter, µg/m³ — the prediction target |
| pm10 | float | Coarse particulate matter, µg/m³ |
| no2 | float | Nitrogen dioxide |
| so2 | float | Sulphur dioxide |
| co | float | Carbon monoxide, mg/m³ |
| o3 | float | Ozone |
| nh3 | float | Ammonia |
| wd_degree | float | Wind direction, 0–360° (coalesced from four sparse aliases) |
| solar_radiation | float | Solar radiation, W/m² — drives ozone formation |
| pressure | float | Barometric pressure, mmHg |
| temperature_c | float | Air temperature, °C |
| humidity_percent | float | Relative humidity, clamped to 0–100 |
| wind_speed_ms | float | Wind speed, m/s — governs dispersion |
| rainfall_mm | float | Rainfall, mm — physically scrubs particulates |
| weather_condition | text | clear / rainy / hot / cold / humid / heavy_rain |
| traffic_index | float | Congestion 0–100, clamped |
| is_rush_hour | int | Commute-hour flag, repaired to strict 0/1 |
| year, month, day, hour | int | Calendar parts of the timestamp |
| day_of_week | int | Day index for weekly cycles |
| is_weekend | int | Weekend flag, repaired to strict 0/1 |
| season | text | monsoon / winter / summer / post_monsoon |
| climate_type | text | City climate class (14 values) |
| urbanization_index | float | City-level urban intensity |
| data_source | text | "real" or "synthetic" — the honesty column |
| source_station | text | Which real station a synthetic row derives from |

## 3.2  How the synthetic rows were generated

Each real station produces eight synthetic sibling stations. Each sibling is a complete, coherent time series derived from the parent by an AR(1) perturbation in continuous time. Five rules distinguish this from the original expansion:

- Only continuous physical measurements are perturbed. Flags, identifiers, categories and timestamps are copied or recomputed, never randomised.

- The noise is autocorrelated with the same decay as the data itself, and the decay is estimated from each station’s own history. This is what preserves temporal structure.

- Gaps are measured in real hours, so a five-hour hole decorrelates five hours’ worth rather than pretending rows are adjacent.

- Every perturbed value is clamped to its physical range.

- The missingness pattern is preserved exactly — if a real reading was absent, so is its synthetic counterpart. Filling gaps is the subtlest way to make fake data look easy, and it is what the original rig did.

Synthetic series are separate stations, never interleaved with real rows under the same identifier. This means the forecasting window never mixes real and synthetic data, and "evaluate on real data only" is a single filter.

## 3.3  Validation results

Measured on 22 paired parent stations covering 6.7 million rows. All five checks pass.

| Property tested | Real | Synthetic | Difference | Result |
| --- | --- | --- | --- | --- |
| Persistence R² (predictability) | 0.8955 | 0.8889 | 0.0065 | PASS |
| Autocorrelation, lag 1 hour | 0.9344 | 0.9322 | 0.0022 | PASS |
| Autocorrelation, lag 6 hours | 0.7452 | 0.7420 | 0.0032 | PASS |
| PM2.5 median | 46.74 | 46.67 | 0.1% | PASS |
| PM2.5 95th percentile | 203.75 | 205.19 | 0.7% | PASS |
| Missingness rate | 27.46% | 27.46% | 0.00 pp | PASS |
| Correlation pm25–pm10 | 0.8715 | 0.8650 | 0.0065 | PASS |

For comparison, the original expansion had a persistence gap of 0.123 — its synthetic rows were dramatically easier to predict than real ones. The new gap is 0.0065, a 19-fold improvement, and missingness now matches exactly.

# 4. Why the Previous Model Scored R² = 0.58

This is the single most important finding in the report, because it explains why the earlier work did not function.

| Approach | R² | RMSE (µg/m³) |
| --- | --- | --- |
| Persistence — "next hour = this hour", no model at all | 0.8056 | 29.59 |
| The previous GBT model | 0.58 | not comparable |

A model that has the current PM2.5 among its inputs cannot mathematically score below persistence unless something upstream is broken. Four causes were found:

| Cause | Explanation |
| --- | --- |
| Labels were ~26% fabricated | PM2.5 was imputed before the prediction target was built, so roughly a quarter of training labels were medians — a constant the features cannot predict. |
| 8.69% of labels had the wrong horizon | The label used a positional "next row" lookup. With gaps in the data it returned rows 2, 3 or 5 hours later and labelled them as one hour. Measured across 479,937 real transitions. |
| Random train/test split leaked | On a time series, hour T lands in training while T+1 lands in test, and consecutive hours are strongly correlated. |
| Silent row deletion | The feature assembler was configured to skip rows with any missing value, which can discard most of the training set without raising an error. |

On the reported RMSE of 0.57: persistence RMSE on raw PM2.5 is 29.59 µg/m³. A value of 0.57 is roughly fifty times smaller, which means the target had been scaled or log-transformed. Such a number is not comparable to anything and cannot be defended. All reporting is now in raw µg/m³.

Safeguard now in place: the training script computes the persistence baseline on the same test rows every run and prints an explicit FAIL with a diagnostic checklist if the model does not beat it.

# 5. Model Results

Measured on 3,779,058 labelled rows with a chronological hold-out, scored on real rows only (n = 190,306).

| Model | Target | R² | RMSE | MAE | Gain vs persistence |
| --- | --- | --- | --- | --- | --- |
| Persistence baseline | — | 0.8984 | 21.695 | 10.059 | — |
| GBT | level (original spec) | 0.9098 | 20.478 | 9.559 | 5.6% |
| GBT | delta (adopted) | 0.9201 | 19.240 | 9.094 | 11.3% |
| XGBoost | delta | 0.9193 | 19.337 | 9.089 | 10.9% |

Key finding on model choice: XGBoost, a more powerful library, did not beat a well-tuned GBT. Changing what the model predicts doubled the gain, while changing the algorithm did nothing. Gradient Boosted Trees remain the correct choice, as the project specification requires.

Decision trees are piecewise-constant and cannot express "next hour is roughly this hour" as a function. Asked to predict the level, the model spends all its capacity rebuilding persistence — its feature importance for PM2.5 was 1.25 while nothing else exceeded 0.04. Predicting the change instead lets every tree model the actual dynamics, and importance then spreads across real physics: previous-hour PM2.5 (0.178), current AQI (0.080), PM10 (0.079), CO (0.047), season (0.030).

Two configuration changes were also made: the number of trees was raised from 20 to 300, and depth from 5 to 6. Twenty trees is drastically undertrained for a feature matrix of this size.

# 6. Hadoop Cluster Configuration

The cluster runs one NameNode and four DataNodes. Four is recommended over three, for a reason that follows directly from the replication arithmetic below.

| Parameter | Value | Derivation |
| --- | --- | --- |
| Dataset size | 27.48 GB | Measured output of the expansion build |
| HDFS block size | 128 MB | Hadoop default |
| Total blocks | 220 | 27.48 GB ÷ 128 MB |
| Replication factor | 3 | Hadoop default; survives two node failures |
| Total block replicas | 660 | 220 blocks × 3 |
| Raw storage required | 82.44 GB | 27.48 GB × 3 |
| NameNode | 1 | Metadata and block map |
| DataNodes | 4 (recommended) | See note below |
| Storage per DataNode | 20.61 GB | 82.44 GB ÷ 4 nodes |
| Input splits for Spark | 220 | One task per block — the unit of parallelism |
| Source files | 23 CSV parts | Each ~1.2 GB, splitting into roughly 10 blocks |

## 6.1  Why four DataNodes rather than three

With three DataNodes and a replication factor of three, every node must hold a copy of every block. That is valid and fault-tolerant, but it has two costs:

- No distribution benefit. Since each node stores the entire dataset, HDFS cannot spread distinct blocks across machines, and each node needs the full 27.48 GB rather than a share of it.

- No re-replication headroom. If one node fails, the cluster drops to two replicas and cannot restore the third until the node returns, because there is nowhere else to place it.

With four DataNodes, blocks genuinely distribute: each node holds roughly 165 of the 660 replicas (about 20.6 GB), reads parallelise across four machines instead of being served from whichever node is least busy, and a single node failure can be fully re-replicated onto the survivors while the cluster stays at three copies.

Three DataNodes is the practical minimum for replication factor 3 and will work correctly. Four is the smallest configuration that behaves like a real distributed cluster.

## 6.2  YARN resource allocation

| Setting | Value | Reason |
| --- | --- | --- |
| spark.executor.memory | 8 GB | Per the project specification |
| spark.driver.memory | 4 GB | Per the project specification |
| Executors per DataNode | 2 – 3 | Leaves memory for the NodeManager and OS |
| spark.sql.shuffle.partitions | 400 – 800 | Roughly 2–4× the total core count; the default of 200 under-parallelises at this data volume |
| Storage level for caching | MEMORY_AND_DISK | Prevents job failure when a partition exceeds RAM |

# 7. Phase-by-Phase Status

| Phase | Objective | Status |
| --- | --- | --- |
| 0. Dataset rebuild (added) | Audit, repair and rebuild the dataset honestly | COMPLETE |
| 1. HDFS upload | Load 27.48 GB into HDFS across 4 DataNodes (220 blocks, 3x replication) | NOT STARTED |
| 2. Spark engine activation | Launch Spark on YARN across the DataNodes | NOT STARTED |
| 3. Data cleaning & processing | Sanitise and structure the data | COMPLETE (logic) |
| 4. Feature engineering | Build the T+1 target and feature matrix | PROVEN LOCALLY |
| 5. GBT training | Train the distributed regressor | PROVEN LOCALLY |
| 6. Evaluation & export | Validate accuracy, export the model | PARTIAL |
| 7. Streaming speed layer | Structured Streaming micro-batch ingestion | NOT STARTED |
| 8. Alert engine | Closed-loop AQI > 150 health warnings | NOT STARTED |
| 9. Hive serving layer | External tables and ad-hoc SQL | NOT STARTED |
| 10. Dashboard | Throughput charts, alert feed, GBT vs RF graph | NOT STARTED |

## 7.1  What is genuinely complete

- Full audit of the original dataset — every column, fill rate and defect measured rather than assumed.

- A rebuilt 27.48 GB dataset that passes five statistical fidelity tests.

- Diagnosis and repair of the four causes of the R² = 0.58 failure.

- Feature engineering logic: validated T+1 target, CPCB AQI, rolling and lag history, cyclical encodings, physical interaction features.

- A trained model that beats the persistence baseline, with results verified on real rows only.

- A model-selection study comparing GBT against XGBoost and two target formulations.

## 7.2  What remains

| Work item | Why it matters | Effort |
| --- | --- | --- |
| Install Spark and run Phases 2–6 distributed | Everything so far was proven on one machine. This is the core Big Data deliverable. | Low |
| Upload dataset to HDFS | Phase 1; enables block splitting and replication. | Low |
| Export trained model to HDFS | Required Phase 6 artefact. | Low |
| Random Forest comparison baseline | The project document promises a GBT-versus-Random-Forest comparison chart. | Low |
| Streaming speed layer | Structured Streaming over micro-batches — a headline novelty claim. | Medium |
| Closed-loop alert engine | Writes warnings when predicted AQI exceeds 150. The stated purpose of the system. | Medium |
| Hive serving layer | External tables plus the analytical queries in the project document. | Medium |
| Dashboard | Throughput charts, comparison graphs, live alert feed. | High |
| Spatial neighbour features | Optional. The largest remaining accuracy gain, and it feeds the GraphX future scope. | Medium |

# 8. Deliverables Produced

| File | Purpose |
| --- | --- |
| 00c_expand_dataset.py | Builds the 27.48 GB dataset from real rows; repairs all four defects |
| 00d_validate_expansion.py | Five-test statistical validator — treat any FAIL as blocking |
| 02_feature_extraction.py | Spark: T+1 target, CPCB AQI, history, cyclical and interaction features |
| 03_train_gbt.py | Spark: chronological split, persistence-benchmarked GBT on the delta target |
| 03b_local_run.py | Single-machine reproduction used to prove the pipeline before cluster submission |
| 01b_build_wide_table.py | Alternative path: converts real US EPA data if fully-real data is ever required |
| 00_fetch_real_data.py | Downloads ~27 GB of real EPA measurements (verified available) |
| COLUMN_DECISION_REPORT.md | Column-by-column justification with measured evidence |
| HONEST_SCALING.md | Expansion methodology, validation results and defence notes |
| _audit/ (7 scripts) | Every measurement in this report, re-runnable |

# 9. Recommended Next Steps

In order:

- Install PySpark and run Phases 2–6 on the real dataset. Java 21 is already present, so this is unblocked. This converts "proven locally" into "Phase 6 complete".

- Upload the dataset to HDFS and export the trained model, closing Phases 1 and 6.

- Add the Random Forest baseline so the promised comparison chart can be produced.

- Build the streaming layer and the alert engine — together these are the project’s stated novelty.

- Build the Hive serving layer and dashboard last, as they depend on everything above.

# 10. A Note on Honesty for the Viva

11.1% of the dataset is real measurement and 88.9% is generated. This should be stated openly rather than avoided. The defensible framing is:

A 27.5 GB benchmark at scale factor 9, generated from 16.25 million real CPCB measurements by a disclosed AR(1) model that is validated to reproduce the real data’s autocorrelation, distribution, sparsity and inter-pollutant correlations. All model evaluation is performed on real rows only.

This is standard practice — the same principle as a TPC-H scale factor in database benchmarking. The systems claims (throughput, block distribution, shuffle behaviour) rest on the full 27.5 GB; the scientific claims rest on the real subset. The two are cleanly separated by the data_source column, and the validator provides the evidence that the generated rows are statistically faithful.